## Sheet1
Project: | AI-Powered ESG Sustainability Score for Companies
Start Date | 14.10.25
End Date | 31.12.25
DAYS NEEDED
Task No | TASK NAME | START DATE | END DATE | PLANNED | ACTUAL
1 | Analyzing the Problem Statement | 14.10.25 | 17.10.25 | 4
2 | Data Collection from Kaggle and another Company Website directly | 18.10.25 | 24.10.25 | 7
3 | Data Cleaning and Preprocessing | 25.10.25 | 31.10.25 | 7
4 | ML model development & evaluation | 01.11.25 | 14.11.25 | 15
5 | Dashboard design & deployment | 15.11.25 | 30.11.25 | 15
6 | Testing, optimization | 01.12.25 | 15.12.25 | 15
7 | Documentation & final report | 16.12.25 | 31.12.25 | 15